## Slide 1: Vessel Triage
Policy Area on Maritime Safety and Security (PA Safe)
Turku, 17 – 18 May 2016
Raita Putkonen, Finnish Border Guard Headquarters

## Slide 2: Project Details
The goal is to promote the integration process of method into the guidelines of the International Maritime Organisation (IMO).
Lead partner: Finnish Border Guard
Estimated duration and deadline: 1.9.2015 - 31.10.2017 (2 years 2 months)
Total funding: 150 000 €
Split by source: The Ministry for Foreign Affairs of Finland with 120 000 €, the Finnish Border Guard with 30 000 €.
Vessel Triage

## Slide 3: Progress since the most recent meeting
Vessel Triage method was published at IMO NCSR 3 (2016) /document 3/21/2
Quotation from the meeting report: Consequently, the group agreed to invite the Sub-Committee to encourage Member States, SAR services and other parties to test the Vessel TRIAGE method and to provide their feedback as appropriate to the email address vesseltriage@raja.fi, so that Finland can take account of their experience in preparing further Vessel TRIAGE documentation.
Vessel Triage

## Slide 4: Future steps to be taken at the IMO
Vessel Triage
First presentation at the IMO
Summary of the testing results to the NCSR 4
Further proceedings at the IMO
Finland will ask support for drafting group

## Slide 5: Progress since the most recent meeting
A scientific article was published in Safety Science:
  http://www.sciencedirect.com/science/article/pii/S0925753516000096
Testing phase (Finnish Border Guard + shipping companies) of the method has started during the autumn 2015 and simulator exercises have been carried out during the winter.
  The feedback received has been mainly positive.
  The Vessel Triage APP will be published in May.
Vessel Triage

## Slide 6: Requests for the Steering Committee members and the Policy Area Coordinators
Vessel Triage

## Slide 7: Thank you for your attention Further information: http://www.raja.fi/vesseltriage

## Slide 8: Baltic Sea Maritime Incident Responce Group (Baltic Sea MIRG) Project
Policy Area on Maritime Safety and Security (PA Safe)
Turku, 17 – 18 May 2016
Raita Putkonen, Finnish Border Guard Headquarters

## Slide 9: Project Details
The project will create joint MIRG coordination models and standard operating procedures for the Baltic Sea region and support the harmonisation of MIRG services in Europe
Lead partner: Finnish Border Guard
Estimated duration: 1.12.2014-31.12.2016
Total funding: 539 800€
Split by source: The Ministry for Foreign Affairs of Finland with 377 500 €; the Finnish Border Guard, together with the Emergency Rescue Services and the Finnish Transport Safety Agency, with 162 300€.
Baltic Sea MIRG

## Slide 10: Project Details
Three Work Packages:
WP 1 - Overview of the current MIRG services and training in Europe (9/2015–8/2016)
WP 2 - Incident analyses (8/2015–4/2016)
WP 3 - Development of joint MIRG coordination models and standard operating procedures (1/2016 – 8/2016)
Baltic Sea MIRG
Picture: VVF Trieste

## Slide 11: WP 1: Progress and challenges since the most recent meeting
Descriptions of different European countries' emergency fire and rescue services at sea and MIRG related training received
 Still waiting for descriptions from some countries
Competence needs required in MIRG operations have been defined to be able to compare different training systems.
Challenges encountered
Baltic Sea MIRG
CATEGORIES OF THE DEFINED MIRG COMPETENCIES:
MARITIME SEARCH AND RESCUE SYSTEM
TRANSFER TO SITE
KNOWLEDGE OF TARGET
TYPES OF OPERATION
Ship fire
Technical rescue tasks
Emergency medical care
Vessel chemical spill

## Slide 12: WP 2: An analysis on European maritime traffic made by the Finnish Transport Safety Agency
Baltic Sea MIRG
- The most of the European ship fires occurred in the North Sea, English Channel and Bay of Biscay (41%).
-The Baltic Sea was ranked third in this comparison, but only 3% of fires were serious.
- Ship fires pose the greatest threat to European maritime safety when the risk is loss of human life or serious injury. Fire poses the greatest threat aboard ro-ro passenger ships.

## Slide 13: WP 2: Ship Fire Analysis
Baltic Sea MIRG
An analysis on the seven past ship fires in which MIRG teams or other forms of external assistance were or could have been deployed.
  1) m/s Calypso (cruise ship), UK, 2006
  2) m/v Lemo (cargo ship), Finland, 2008
  3) m/s Commodore Clipper (ropax vessel), UK, 2010
  4) m/s Pearl of Scandinavia (ropax vessel), Sweden, 2010
  5) m/s Nordlys (ropax vessel), Norway, 2011
  6) m/v Fernanda (ro-ro vessel), Iceland, 2013
  7) m/v Purple Beach (cargo ship), Germany, 2015

## Slide 14: WP 2: Recommendations made in the Ship Fire Analysis
Baltic Sea MIRG
Coastal countries should have the readiness to dispatch MIRG teams and use them flexibly.
There should be agreements to use MIRG Liaison officers in the RCC.
The co-ordination and command structure of external help used in ship fires should be clarified.
Base locations, transport logistics and on-call arrangements of MIRG units and SAR helicopters should be developed as a whole.
Joint ship fire drills between vessels and MIRG teams should be developed.
Redundancy in division of work related emergencies on ships should be developed to withstand the absence of individual key persons.

## Slide 15: WP 3: SOPs being developed
Vessel Triage
Occupational safety
Distress Vessel
Requesting assistance
The Role of MIRG Operations Commander
The Role of MIRG/Fire Liaison Officer
Communications during international MIRG operations
Completion of operations – return journey
Baltic Sea MIRG

## Slide 16: WP 3: Cooperation with shipping companies
Baltic Sea MIRG

## Slide 17: Thank you for your attention Further information: http://www.raja.fi/MIRG