## Slide 1: WINMOS – Winter Navigation Motorways of the Sea
Policy Area on Maritime Safety and Security (PA Safe)
Turku, 17 – 18 May 2016
Emmi Saarinen / Swedish Maritime Administration / Finnish Transport Agency

## Slide 2: Project Details
The main objectives: to develop the maritime winter navigation system and to safeguard required icebreaking recourses in the future.
Implementing period 2012 – 2015.
Implementing countries Sweden, Estonia and Finland (9 partners).
Budget 139 MEUR, contribution from EU 29,6 MEUR.
Activities
  Activity 1 – Study on future demand for icebreaking capacity
  Activity 2 – Concept study on next generation icebreakers
  Activity 3 – Improvement of environmental performance
  Activity 4 – Next generation IBNet
  Activity 5 – Human element and training
  Activity 6 – Technical upgrading and life extension of icebreakers
  Activity 7 – Acquisition of a new icebreaker
WINMOS

## Slide 3: Progress and challenges since the most recent meeting
Activity 1 – Holistic operational simulation model + holistic economic cash-flow model → eg. total cost of winter navigation and individual cost of icebreakers, future development trends.
Activity 2 – Several studies eg. fuelling possibilities, model tests and comparison between models, different ownerships and operating arrangements → optimal future icebreaker fleet.
Activity 3 – New fuelling technique (Common Rail) tested on icebreaker YMER → fuel saving 7.3% and black carbon almost completely disappeared.
  Due to technical problems all five engines could not be fitted with new system during project implementation.
WINMOS

## Slide 4: Progress and challenges since the most recent meeting
Activity 4 – IBNext solution fully browser based which can be utilized with any device that has a modern web browser.
Activity 5 – Training programme and enhanced simulator functions.
Activity 6 – Life extension programme on four Swedish icebreakers ables them to operate for 10 – 15 years longer.
Activity 7 – World’s first LNG fuelled icebreaker named Polaris.
  Delayed due to trade sanctions between Russia and EU.
  Sea trials ongoing.
Final seminar presentations available online: www.winmos.eu/reports/
WINMOS

## Slide 5: Future activities – WINMOS II
Aims to further develop and enhance the winter navigation system and its safety, and to safeguard required icebreaking resources in the future by developing new options and improving old capacity by meeting modern day environmental standards.
Activities
  Activity 1 - Design study of next Swedish icebreaker
  Activity 2 - Implementation and further development of IBNext
  Activity 3 - Battery hybrid for safer and more environmentally friendly operation
  Activity 4 - Further development of the Common Rail system
  Activity 5 - Life extension of Finnish icebreakers
  Activity 6 - Study on removable-bow concept
  Activity 7 - Development of icebreaker training
  Activity 8 - Study on life extension of Estonian icebreakers
  Activity 9 - Study on adequacy of icebreaking capacity and level of service in Baltic Sea during severe winters
  Activity 10 - Project management and dissemination
WINMOS

## Slide 6: Thank you for your attention Further information: www.winmos.eu