## Slide 1: EUSBSR PA Ship 6th international Steering Committee meeting
Progress report of the BONUS SHEBA project
14. April 2016 / Copenhagen
Markus Quante, HZG
Jana Moldanova, IVL
Sustainable Shipping and Environment of the Baltic Sea region

## Slide 2: SHEBA Consortium
Sweden
Swedish Environmental Research Institute (IVL), Gothenburg
Chalmers University of Technology (Chalmers), Gothenburg
Swedish Defence Research Agency (FOI), Stockholm
Germany
Helmholtz-Zentrum Geesthacht, Centre for Materials and Coastal Research (HZG), Geesthacht
Ecologic Institute (EI), Berlin
Finland
Finnish Meteorological Institute (FMI), Helsinki
Finnish Environment Institute (SYKE), Helsinki
Estonia
Marine Systems Institute, Tallinn University of Technology (TUT), Tallinn
Poland
Maritime Institute in Gdansk (MIG), Gdansk
Denmark
University of Southern Denmark, Department of Environmental and Business Economics, (SDU), Esbjerg
France
Centre National de la Recherche Scientifique, Marseille Interdisciplinary Centre for Nanoscience, joint research unit UMR 7325 (CNRS/CINAM), Marseille

## Slide 3: SHEBA Objectives and Structure
Objectives
The aim of Sheba is to provide an integrated and in-depth analysis of
the ecological,
economic
and social impacts
of shipping in the Baltic Sea and to support development of the related policies on EU, regional, national and local levels
Runtime
SHEBA is running from April 1st 2015 to
March 31st 2018

## Slide 4: SHEBA progress report
SHEBA has now been running for 1 year and all partners are actively involved in diverse working items throughout the project.
Here progress is reported concerning activities connected to:
    Policy, Scenarios, Activity data
    Air pollution modelling
    Water pollution
    Underwater noise
    Stakeholder meeting
    Stakeholder elicitation
    Measurement campaign
    outreach activities

## Slide 5: WP1 Policy, Scenarios, Activity data
A report ‘Drivers for the shipping sector’ has been completed. This analysis is used for the scenario work in SHEBA.
(can be downloaded on Sheba webpage www.sheba-project.eu/deliverables/index.php.en)
AIS-based commercial shipping activity data has been prepared in WP1 for use in the current and scenario emission inventories of air and water pollutants and underwater noise.
Predicted annual sum of NOx emission (as NO2) due to Baltic Sea shipping in 2007. Emissions are given as tons/grid cell.
MarineTraffic
12/04/16 10 am

## Slide 6: WP1 cont.
Leisure boar fuel consumption in kg/grid cell/year (Johansson, 2016)
Database with activity data for recreational shipping is in progress and will be ready in few months.
A meeting focusing on the construction of scenarios in SHEBA and on the assessment DPSIR framework was held in Berlin in February 2016 (together with WP5).
WP1 is participating in a scenario workshop in Helsinki organized by the Bonus project BALTICAPP.
Scenario years:
2030 / 2040
Topics:
BAU / SECA / NECA
Modal shift
Zero into water
Slow steaming, Port installtions
etc. …
Notes: DPSIR (Abkürzung für Driving forces, Pressures, States, Impacts and Responses

## Slide 7: WP2 Air pollution
Shipping contribution to PM air concentration and NOx deposition in the North Sea and Baltic Sea areas: a) PM2.5 in µm m-3, b) PM2.5 in %, c) total deposition of N in mg m-2 , d) total deposition of N in % (Image adapted from Jonson et al. 2015).
WP2 has made progress with setting up chemistry transport model systems in the project.
An ensemble of 3 atmospheric models to simulate contributions of shipping to air pollution levels and deposition on land and the sea surface will be used.
→ both in current situation (2008, 2011, 2013)
and for scenarios
HZG: CMAQ Set-up
plus
IVL EMEP-TAPM
FMI SILAM CTM

## Slide 8: WP2 cont.
Air quality models on city scale:
TAPM (IVL) [coupled to EMEP]: 1x1 km2, Västra Götaland
TAPM (HZG) 200x200 m2, 4 harbours
CMAQ (HZG) 1x1 km2, 4 harbours
CityChem (HZG) [coupled to CMAQ]
1x1 km2, 4 harbours
STEAM
emission model
AIS ship data
250x250 m2
City-scale air quality modelling

## Slide 9: WP 3 Water pollution
WP3 has analysed the shipping-related sources of pollutants and the availability of data, both in terms of emission factors and environmental impacts.
Distribution of water pollutants will be calculated with help of AIS-based model STEAM (WP1) which will implement emission factors provided by WP3.
Preparation of a measurement campaign is in progress. Goal: investigating pollution fingerprints in shipping lanes of the Baltic Sea using the sailing research vessel Hrimfare for the second half of June.
Ecosystem model – test runs conducted at TUT.

## Slide 10: WP 4 Underwater Noise
Example of a noise source description of a vessel.
Note the low frequency hump, which is due to
bad propeller design
1. Description of shipping noise sources
2. Sound propagation under water
3. Impacts to marine life
- Modeling
- Measurements of underwater noise
- Observations of behavioral changes of fish using
a controlled experiment in a natural environment
WP4 has prepared the methodology for description of shipping induced noise parameters which will be implemented into the STEAM model.
A noise fingerprint library is under construction.
(deliverable: database)
Location of the fish pen will be the Tvärminne zoological station (59.845572N, 23.248574E), Hanko, Finland.
(herring, perch, roach, pike perch )
Notes: Perch: Barsch, Pike perch: Zander, Roach: Rotauge;

## Slide 11
Noise: Are there conflicting interests?
Plan Bothnia project; Planning the Bothnian Sea, 2013

## Slide 12: Stakeholder meeting in Hamburg
In September 2015 the Helmholtz-Zentrum Geesthacht hosted the 1st SHEBA stakeholder meeting in Hamburg, where about 20 stakeholders of the shipping sector participated.
The meeting was organized in form of World Cafés with topics:
Air pollution
Water pollution
Underwater noise
Scenario development
Current policy mix
Future shipping in the Baltic
Outcomes are available in the ‘Brief from the SH meeting’
via www.sheba-project.eu/Deliverables and in Sheba’s Newsletter nr. 2.

## Slide 13: Further stakeholder elicitation
A need for additional workshops with stakeholders was identified during the 1st SH meeting. Extra funding to organize 2 additional SH workshops has been received from Swedish Institute.
Sheffield Elicitation Framework (SHELF)
(quantifying expert knowledge)
Training workshop 25-27 May in Gothenburg
Dedicated SH meetings:
September 2016 in Tallin
Spring 2017 in Gdansk
Autumn 2017 in Gothenburg
Professor Tony O`Hagan
University of Sheffield

## Slide 14: Measurement campaign in summer 2016
SHEBA has scheduled a field campaign in
summer 2016 with the research sailing ship Hrimfare
(20 June to 2 July)
Nutrients,
Contaminants
(oil residues, other organic contaminants, metals)
Marine microlitter and ship related particles (1µm – 5mm)
pH, alkalinity
TOC (total organic carbon)
Air pollutants from shipping with focus on particles
Parameters to be measured:
Measurements will be done in the water column and in air along transects crossing important shipping lanes
Approximate
sampling area
Ship traffic in the Baltic during one day in Nov. 2008
Black lines = tankers blue lines = passenger ships
red lines = cargo

## Slide 15: Outreach activities in connection with the measurement campaign
Presentation of SHEBA and other BONUS projects will be held at the Swedish ”Politicians’ week” (Almedalsveckan) on Gotland, 2-6/7, and the Danish ”People’s meeting” (Folkemöde) on Bornholm, 16-19/6.
These meetings are important platforms in Sweden and Denmark for political discussions.
The visitors are politicians, business people, NGOs and other organizations, and also the general public.

## Slide 16: Meetings
During this first year the project has organized 2 consortium meetings.
The first was a kick-off meeting in May 2015 hosted by Chalmers in Gothenburg which gathered the project partners, the SHEBA external advisory board and a representative of the Bonus secretariat.
The second meeting was hosted by the Helmholtz-Zentrum Geesthacht in Hamburg in September 2015 prior to the stakeholder meeting.
The next consortium meetings are planned for
18-20 May 2016 in Helsinki
7-9 September 2016 in Tallin.
Alliance
SHEBA has become a flagship project of EUSBSR and an affiliated project of Baltic Earth (www.baltic-earth.eu).