## Slide 1: CompMon - Compliance monitoring for Marpol Annex VI
5th PA Ship Steering Committee meeting

## Slide 2: Main objectives of CompMon
To join Member States’ forces in voluntary piloting of effective targeting for the enforcement of IMO Marpol Annex VI
To pilot the enforcement in MS territories at sea
To share best practices in the implementation of targeting methods
To communicate the experiences to e.g. regional conventions

## Slide 3: Partners
Member states authorities responsible for the enforcement of the sulphur directive:
Finland, Sweden, Netherlands, Belgium
Implementing organizations:
Finnish Transport Safety Agency, Finnish Meteorological Institute, Åbo Akademi University (FI), Chalmers University (SWE), Transportstyrelsen (SWE), Human Environment and Transport Inspectorate (NL), FOD Mobiliteit en Vervoer (BE) and Royal Belgian Institute of Natural Sciences

## Slide 4: What has been done:
Flight certification (STC) of compliance monitoring system in Piper Navajo
Short SC.7 Skyvan of Aalto University has been equipped with updated sensors for CO2 and SO2.
Development of software for automatic compliance measurements detection
Sulfur compliance measurement at a fixed station in Göteborg ship channel between Jan 2014 to Nov 2015, (>4000 inspections)
Sulfur compliance measurement in Belgium by Normand Britten Islander (OO-MMM aircraft). One week campaign of compliance measurements (161 inspections).
Notes: In addition, Skyvan will be equipped with particle sensors.

## Slide 5: What has been done:
Sweden has purchased two hand-equipment for quick scanning on board vessels. Training of the inspectors is on-going.
In The Netherlands quick analysis equipment has been in use since 2014.
Legal study on sulphur directive in Finland. This legal study will be utilized in CompMon legal analysis.
Fixed installation onboard Finnish Border Guard LNG-powered vessel Turva. Installation is complete, but not yet active.
FMI has made an emission estimate tool that is used in optical monitoring instruments.
Notes: Trafi will procure two handheld analysis devices as well in 2016. Experiences of these devices will be shared throug a summary report.

## Slide 6: What has been done:
Associated activities which are financed outside the project directly by the Danish Environmental Protection Agency:
  Sulfur compliance measurement at Great Belt bridge between June 2015 to Nov 2015, (3000 inspections)
  Airborne Sulfur compliance measurement around the coasts of Denmark using a Piper Navajo aircraft(OY-MST) between June 2015 to Nov 2015, (600 inspections)
Notes: Chalmers University provides sulphur comliance monitoring to Danish EPA.

## Slide 7: What’s going on:
Trafi’s call for tenders on monitoring service of sulphur compliance is soon to be published.
CEF-funding: Signature process to be finalized next week
ILT is working on a fixed or mobile sniffer in Dutch ports as Flushing, Amsterdam and Groningen
Co-operation between The Netherlands and Belgium for aerial inspections
Notes: Trafi has prepared the call this autumn and it is planned to be published before Christmas.
After the signature, we can focus on future activities (next slide). To some activities CEF-funding is critical and after the signature the whole project will be fully implemented.

## Slide 8: Next steps:
Stakeholder conferences
Work on CompMon legal analysis
CompMon website
CompMon promoting tour in Baltic sea MS
Airborne surveillance in North Sea will continue with more flight hours
ILT is developing fuel calculator for onboard inspections verifying the fuel record books

## Slide 9: Next steps:
Onboard emission monitoring
Developments of electronic fuel record book connected with AIS track data for inspection
Upgrading of sensors, software and telecommunications of a long term air quality reference station on Utö island (Finland)
FMI will create and manage two knowledge databases that will be used for quality assurance of compliance monitoring information
…
Notes: Automatic Identification System (AIS) is an automatic tracking system used on ships and by vessel traffic services (VTS) for identifying and locating vessels by electronically exchanging data with other nearby ships.

## Slide 10
"The sole responsibility of this publication lies with the author. The European Union is not responsible for any use that may be made of the information contained therein."